## Features
Feature ID | Priority | Feature | Est | Desc | Date Added | Date Prioritized
1 | 10 | Product Search | 2 | Search page for Products
8 | 17 | Product Matrix | 2 | Product matrix page for search results or category listing
2 | 20 | Product Detail Page | 1 | Display of product details
3 | 30 | Admin Login | 4 | Ability for an administrator to login
4 | 40 | Product Edit Page | 3 | Edit the general product detals and category
5 | 50 | Category Edit | 2 | Add/Edit/Deleet category name, description, and picture
7 | 55 | RELEASE 1! | 0.5
6 | 60 | Push product data to System Y | ? | Push product data to other system on [daily?¦immediate?]

## Task Tracking
Feature
|  |  |  | Done? | Iteration | Task ID | # | Priority | Name | Estimate | Remaining | Task Description
|  |  |  | 1 | I1 | 1A | 1 | 10 | Product Search | 3 | 0 | Create DAL objects and product tables in DB
Iteration | Assigned | Capacity | % | 1 | I1 | 1B | 1 | 10 | Product Search | 2 | 0 | Create search form
I1 | 56 | 60 | 93.33% | 1 | I1 | 1C | 1 | 10 | Product Search | 4 | 0 | Implement search function and results display using matrix
I2 | 46 | 60 | 76.67% |  | I1 | 8A | 8 | 17 | Product Matrix | 8 | 8 | Implement matrix control to display products and fire paging events
I3 | 0 | 42 | 0% |  | I1 | 2A | 2 | 20 | Product Detail Page | 3 | 3 | Create page
[5 empty] | I1 | 2B | 2 | 20 | Product Detail Page | 2 | 2 | Wire up data objects + query
[5 empty] | I1 | 3A | 3 | 30 | Admin Login | 2 | 2 | Update master pages and base page to include properties/link
[5 empty] | I1 | 3B | 3 | 30 | Admin Login | 8 | 8 | Implement membership using sample project pages
[5 empty] | I1 | 3C | 3 | 30 | Admin Login | 12 | 12 | Convert all pages over to site style + layout
[5 empty] | I1 | 4A | 4 | 40 | Product Edit Page | 4 | 4 | Create page and forms for product edit page
[5 empty] | I1 | 4B | 4 | 40 | Product Edit Page | 4 | 4 | Wire page for loading/save
[5 empty] | I1 | 4C | 4 | 40 | Product Edit Page | 1 | 1 | Add edit link to products (page + matrix) for admins only
[5 empty] | I1 | 4D | 4 | 40 | Product Edit Page | 3 | 3 | Add business rule + data validation to product save
[5 empty] | I2 | 4E | 4 | 40 | Product Edit Page | 6 | 6 | Add basic image upload capability (single size) w/ forced resize to max height or width
[5 empty] | I2 | 5A | 5 | 50 | Category Edit | 3 | 3 | Create page/forms for page
[5 empty] | I2 | 5B | 5 | 50 | Category Edit | 1 | 1 | Wire in edit link next to categories for admins
[5 empty] | I2 | 5C | 5 | 50 | Category Edit | 4 | 4 | Wire page for loading/save w/ basic validation
[5 empty] | I2 | 5D | 5 | 50 | Category Edit | 4 | 4 | Add image upload like product image upload
[5 empty] | I2 | R1 | 7 | 55 | RELEASE 1! | 4 | 4 | DB deploy, site build + deploy, production folder setup for images, etc
[5 empty] | I2 | 6A | 6 | 60 | Push product data to System Y | 4 | 4 | Determine reqs for data sync
[5 empty] | I2 | 6B | 6 | 60 | Push product data to System Y | 20 | 20 | Implement something? Need to know reqs to decide method

## Progress Tracking
Start Date |  |  | 2011-06-01
Iteration | Date | Ideal Avail | Ideal Remaining | Actual Remaining | Right Now
I1 | 2011-06-01 | 6 | 54 | 56 | 47
I1 | 2011-06-02 | 6 | 48 | 47 | 47
I1 | 2011-06-03 | 6 | 42 |  | 47
I1 | 2011-06-06 | 6 | 36 |  | 47
I1 | 2011-06-07 | 6 | 30 |  | 47
I1 | 2011-06-08 | 6 | 24 |  | 47
I1 | 2011-06-09 | 6 | 18 |  | 47
I1 | 2011-06-10 | 6 | 12 |  | 47
I1 | 2011-06-13 | 6 | 6 |  | 47
I1 | 2011-06-14 | 6 | 0 |  | 47 | 6.2222 | Corrected Ideal Avail/Day
I2 | 2011-06-15 | 6 | 54 |  | 46
I2 | 2011-06-16 | 6 | 48 |  | 46
I2 | 2011-06-17 | 6 | 42 |  | 46
I2 | 2011-06-20 | 6 | 36 |  | 46
I2 | 2011-06-21 | 6 | 30 |  | 46
I2 | 2011-06-22 | 6 | 24 |  | 46
I2 | 2011-06-23 | 6 | 18 |  | 46
I2 | 2011-06-24 | 6 | 12 |  | 46
I2 | 2011-06-27 | 6 | 6 |  | 46
I2 | 2011-06-28 | 6 | 0 |  | 46 | 0 | Corrected Ideal Avail/Day
I3 | 2011-06-29 | 6 | 36 |  | 0 |  |  | Iteration | I1
I3 | 2011-06-30 | 6 | 30 |  | 0
I3 | 2011-07-01 | 6 | 24 |  | 0 |  |  | Row Labels | Sum of Ideal Remaining | Sum of Actual Remaining
I3 | 2011-07-04 | 6 | 18 |  | 0 |  |  | 2011-06-01 | 54 | 56
I3 | 2011-07-05 | 6 | 12 |  | 0 |  |  | 2011-06-02 | 48 | 47
I3 | 2011-07-06 | 6 | 6 |  | 0 |  |  | 2011-06-03 | 42
I3 | 2011-07-07 | 6 | 0 |  | 0 |  |  | 2011-06-06 | 36
[8 empty] | 2011-06-07 | 30
[8 empty] | 2011-06-08 | 24
[8 empty] | 2011-06-09 | 18
[8 empty] | 2011-06-10 | 12
[8 empty] | 2011-06-13 | 6
[8 empty] | 2011-06-14 | 0
[8 empty] | Grand Total | 270 | 103
Formulas:
Date = [Date, row above]+ IF(WEEKDAY([Date, row above]) = 6,3,1)